## Read first
One-page risk picture — version 1.0, 2026-09-05
Licence: CC BY 4.0. Reuse and adapt with attribution to GRCIDE.
What this is. One page a board or executive committee can decide from. The Risk picture sheet is the page: five to seven rows, each with an owner role, a position against appetite, a direction of travel and the decision requested. The Metrics sheet holds the measures behind the page. The Decision log carries every decision across cycles until it closes. Everything else — the full register, incident detail, programme status — belongs in an appendix, not on the page.
How to fill it. Delete the example rows first; every one of them is invented and prefixed EXAMPLE - delete. Write risk statements as source, event and consequence, and keep the row-level analysis in the risk register rather than here. Position against appetite and trend are closed lists: pick 1, 2 or 3 and do not invent a fourth value. A row at 3. Beyond carries either a funded treatment or a dated acceptance, and the Decision requested column says which.
Two rules the columns enforce. A row with no decision requested is information, and information belongs in the appendix. And a decision is only recorded when Decision taken and Date are both filled, by the body that holds the right to take it.
Metrics. Keep the set small and keep each definition still. A measure earns its place when a failing value forces a decision. Publish the trend across at least three consecutive periods rather than a single value, and agree the target with the owner role before the measure is reported.
What this file does not contain. No personal data, no organisation names, no macros. The example rows are invented and describe no real organisation, risk or decision. This is method material published by an independent publication. It is not legal advice.
Template page: https://grcide.com/templates/one-page-risk-picture
Companion playbook: https://grcide.com/playbooks/board-reporting-for-security

## Risk picture
ID | Risk statement (source, event, consequence) | Business impact | Position against appetite | Trend | Owner (role) | Decision requested | Due | Decision taken | Date
R-001 | EXAMPLE - delete. A contractor keeps standing administrative access after the assignment ends, so changes to the payment platform can be made and go unnoticed. | Unauthorised change to payment configuration, and a loss of transaction integrity that would be reportable. | 3. Beyond | 3. Worsening | Head of platform engineering | Fund automated deprovisioning, or accept the exposure with a named expiry date. | 2026-11-30
R-002 | EXAMPLE - delete. One supplier hosts the customer identity service with no tested exit route, so an outage or an exit stops customer sign-in. | Customer sign-in unavailable, and the agreed availability commitment missed. | 2. At | 2. Stable | Head of customer operations | Approve the budget to cost and test an exit route this period. | 2027-01-31
R-003 | EXAMPLE - delete. Restoration of the case-management database is tested once a year, so an untested change can make recovery fail when it is needed. | Recovery beyond the agreed objective for a service the organisation depends on. | 1. Within | 1. Improving | Head of infrastructure | None this cycle. Reported for information, with the next test date shown. | 2026-12-15 | Noted. Quarterly restore tests confirmed as the standing arrangement. | 2026-09-04

## Metrics
Metric | What it measures | Target | Current | Source | Frequency | Owner (role)
EXAMPLE - delete. Privileged accounts reviewed within the quarter | Whether the access review actually runs on every privileged account. | 100 per cent | 92 per cent | Identity platform export | Quarterly | Head of identity
EXAMPLE - delete. Critical vulnerabilities open beyond the published window | Whether remediation holds to the window the organisation published. | 0 | 4 | Vulnerability management platform | Monthly | Head of infrastructure
EXAMPLE - delete. Suppliers in scope whose assurance is older than the agreed interval | Whether supplier monitoring continues after onboarding. | 0 | 7 | Supplier register | Quarterly | Head of procurement

## Decision log
Date | Decision | Risk ID | Decided by (role) | Follow-up | Status
2026-06-12 | EXAMPLE - delete. Approved the risk acceptance criteria and the appetite statement for the coming year. |  | Executive committee | Publish the criteria and apply them to the register before the next cycle. | Closed
2026-06-12 | EXAMPLE - delete. Accepted R-002 at its current level until 2027-01-31, on condition that an exit route is costed. | R-002 | Chief operating officer | Cost the exit route and report at the next meeting. | Open
2026-09-04 | EXAMPLE - delete. Funded automated deprovisioning of contractor accounts on the payment platform. | R-001 | Executive committee | Deliver by 2026-11-30 and report the measure at the next cycle. | Open